## Execution Timeline
| 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-10-07 | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-09 | Due Date
Status Update 1
PCB- Schematic Design
MCU- Board & Software Acquired | [15 empty] | 2025-10-01
Scan Filter- Filter Framework | bar: 2025-09-02 to 2025-09-16
UI- Software Outline | bar: 2025-09-02 to 2025-09-16
Status Update 2 | 2025-11-11: Not Started
PCB- Component Selection
MCU- Sample data & simulations | [15 empty] | 2025-10-21
Scan Filter- DICOM/ECG synchronization | bar: 2025-09-23 to 2025-10-14
UI- Desktop App
Status Update 3 | 2025-11-11: In Progress
PCB- Board Design
MCU - Dev board simulations | [15 empty] | 2025-11-04
Scan Filter- ECG Steady-State Detection | bar: 2025-10-14 to 2025-10-21
UI- Database and Web App
Status Update 4 | 2025-11-11: Completed
PCB- Test
MCU- Dev Board Fully Programmed
Scan Filter- Functioning Filter | bar: 2025-11-04 to 2025-11-11
UI- Start to Finish File Transfer
Status Update 5
PCB- Combine w/ Hardware | bar: 2025-11-11 to 2025-11-18
Final Design Presentation | [15 empty] | 2025-11-18 | bar: 2025-11-11 to 2025-11-18
Final System Demo | [15 empty] | 2025-12-02 | bar: 2025-12-02
Final Report | [15 empty] | 2025-12-06 | bar: 2025-11-25 to 2025-12-09

## Validation Plan
Paragraph # | Test Name | Success Criteria | Methodology | Status | Responsible Engineers