## Sheet1
| 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | Ownership | Due Date
Status Update 1 | [16 empty] | 2026-01-21
PCB- Updated Design | 2026-04-06: Andrew; 2026-04-20: Not Started
MCU- Subsystem fully functional | 2026-04-06: Lance; 2026-04-20: In Progress
Scan Filter- Arrythmia Gating Fixes | 2026-04-06: Harin; 2026-04-20: Completed
UI- Final Demo Fixes | 2026-04-06: Simon; 2026-04-20: Late
Radar- Programming Plan | 2026-04-06: Simon/Harin
Status Update 2 | [16 empty] | 2026-02-04
MCU & PCB- Ordered | 2026-04-06: Lance/Andrew
Scan Filter- Echo Integration with MRI | 2026-04-06: Harin
UI- DICOM Metadata Implemented | 2026-04-06: Simon
Radar- Program Radar Function | 2026-04-06: Lance/Andrew
Status Update 3 | [16 empty] | 2026-02-18
PCB- Soldered | 2026-04-06: Andrew
Radar - Complete functional testing | 2026-04-06: Lance
Scan Filter- MR Solutions Single Input | 2026-04-06: Simon/Harin
UI- Python.NET Environment Setup | 2026-04-06: Simon/Harin |  | 2026-03-04
Status Update 4
Hardware Fully Operational | 2026-04-06: Lance/Andrew
Radar - Fully Configured & Calibrated | 2026-04-06: Lance/Andrew
Scan Filter-MCU Integration Tests | 2026-04-06: Simon/Harin
UI- Python-C Integration | 2026-04-06: Simon/Harin |  | 2026-03-18
Status Update 5 | bar: 2026-01-12 to 2026-04-06
Software- Validated with test data from hardware | 2026-04-06: Simon/Harin
Radar - Fully validated | 2026-04-06: Lance/Andrew
Final Design Presentation | 2026-04-06: 2026-04-19
Final System Demo | 2026-04-06: 2026-04-27
Final Report

## Copy of Sheet1
| 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | Ownership | Due Date
Status Update 1 | [11 empty] | 2026-01-21
PCB- Updated Design | 2026-03-23: Andrew; 2026-04-06: Not Started
MCU- Subsystem fully functional | 2026-03-23: Lance; 2026-04-06: In Progress
Scan Filter- Arrythmia Gating Fixes | 2026-03-23: Harin; 2026-04-06: Completed
UI- Final Demo Fixes | 2026-03-23: Simon; 2026-04-06: Late
Radar- Programming Plan | 2026-03-23: Simon/Harin
Status Update 2 | [11 empty] | 2026-02-04
MCU & PCB- Ordered | 2026-03-23: Lance/Andrew
Scan Filter- Echo Integration with MRI | 2026-03-23: Harin
| 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16
Status Update 3 | [11 empty] | 2026-02-18
PCB- Soldered | 2026-03-23: Andrew
Radar - Complete functional testing | 2026-03-23: Lance
Scan Filter- MR Solutions Single Input | 2026-03-23: Simon/Harin
UI- Python.NET Environment Setup | 2026-03-23: Simon/Harin |  | 2026-03-04
Status Update 4
Hardware Fully Operational | 2026-03-23: Lance/Andrew
Radar - Fully Configured & Calibrated | 2026-03-23: Lance/Andrew
Scan Filter-MCU Integration Tests | 2026-03-23: Simon/Harin
UI- Python-C Integration | 2026-03-23: Simon/Harin |  | 2026-03-18
Status Update 5 | bar: 2026-02-16 to 2026-03-23
Software- Fully Readable Scans Received | 2026-03-23: Simon/Harin
Radar - Reading Biometric Data Properly | 2026-03-23: Lance/Andrew
Hardware - Testing Completed | 2026-03-23: Lance/Andrew
Final Design Presentation | 2026-03-23: 2026-04-19
Final System Demo | 2026-03-23: 2026-04-27
Final Report